# KPMG Audit AOC and CAO for HCRPT – Recommendation Action Plan

| Rec. # | Recommendation | Action | Due |
| --- | --- | --- | --- |
| 1 CR 2 | The AOC Manual should be reviewed and updated to better reflect the entry control activity undertaken by CASA. The manual need not be prescriptive in the steps to be followed, but should provide minimum requirements and direction on how to address the risks associated with entry control activity. The manual should be prepared as an electronic document with links to electronic forms and with search functionality. In the event that CASA chooses to persevere with the AOC Manual until the results of ASRIP are known, then interim CMIs should be issued to clarify the expectations of CASA in relation to processing subsequent issues of AOC’s. | RSD to review and update AOCM, with Compliance Division input Review and implement current manual amendment processes has been conducted under the overview of the Executive Operations Committee. Produce CMI to better articulate entry and subsequent re-entry control assessment criteria - based on the level of risk represented by that application. A prototype electronic manual with enhanced search capability is a part of the ASSP manual project, with a view of this becoming a corporate standard, if successful. | Jan 2003 Complete July 2002 Sep 2002 |
| 2 CR 3 | While CMIs are used to provide additional guidance on the conduct of entry control activity, there needs to be structured communication channels to ensure all staff are advised of changes to policies and procedures. The CMIs should be easily accessible on CASA’s intranet and any change to the set of CMIs should be summarised and provided to relevant management and staff electronically via a distribution list, which is updated on a regular basis. Managers should be reminded of the need to include new CMI’s as an item on the agenda of all Management, Team Leader and technical staff meetings. | Reinforce current practices for the communication of new and amended Compliance Management Instructions (CMI’s) to staff at local and management meetings. Review processes relating to advising Compliance Division staff of changes to CMI’s. Project for the development of an Intranet site for Compliance Division personnel to include more effective distribution of CMI’s Review effectiveness of new distribution channels for new CMI’s | Complete May 2002 July 2002 Sep 2002 |
| 3 BIR | CASA should record AOC and COA data on a reliable, central database which should provide a facility for flagging upcoming expiries. CASA should be scheduling AOC/COA entry activity, including the sending of expiry advice letters, surveillance activity, if necessary, and quality review time, wherever possible. This should be a central system so that both the airline offices and central office can access it to determine the status of AOC and COA holdings and activity. The recent implementation of Pentana in each of the airline offices is a significant step towards achieving the benefits that such a system would provide. | Establish Pentana User Group. Purpose of the user group is to refine the functionality of Pentana to meet business needs. Develop a database/spreadsheet to centrally store Air Operator Certificate (AOC)/ Certificate of Approval (COA) data. Review processing systems for consistency as the project is developed. Including: - Validation and maintenance of data - Access from all locations - Processes and restrictions for use - Interaction with existing databases Incorporate instructions into the CMI on Air Operators Certification Manual (AOCM)usage. This CMI will require Air Operator Certificate (AOC) expiry notification letters to be sent. Amend AOCM to include to include the intent of the above CMI. Develop an integrated Information Technology strategy. | Complete Scope July 2002 July 2002 Jan 2003 |
| 4 CR 2 | Backdating of Air Operator Certificates should not occur under any circumstances and we support the current GMAO’s refusal to approve such action. | As the GMAO is the only person within Airline Operations who issues such certificates no backdating of documents will occur. | Complete |
| 5 CR 3 | Costs of AOC and COA activity should be recovered from all Operators in a consistent manner and in accordance with the AOC Manual. | Instruction to Managers and staff of the requirement to follow the AOCM. | June 2002 |
| 6 CR 2 | CASA should ensure that all Operators have current and appropriate CLI prior to an AOC issue. In the event that the Enforcement and Investigations Branch identify an Operator that has failed to obtain/renew appropriate CLI, the relevant Airline Office Manager should be advised immediately. | Note: Current legislation does not permit CASA to refuse to issue an AOC if an operator does not have Carriers Liability Insurance (CLI). Refer section 28 Civil Aviation Act 1988. Include in the CMI relating to AOCM usage, an amended form 069 (AOC issue check sheet). This form will include a reference to a CLI check. Improve periodic reporting to incorporate summary of CLI status of operators. Note, lack of CLI may serve as an indicator of risk. Develop a CMI relating to the issuance of Tasking Instructions to assemble a team to assess applications for AOC’s. This CMI will also request the involvement of CLI section from the outset of the AOC process. | July 2002 May 2002 July 2002 (draft complete) |
| 7 BIR | CASA should consider the value of undertaking a financial assessment by reviewing the effectiveness of the assessments and assessing the risks of not completing them. If a financial assessment of an Operator is considered appropriate to mitigate risks to CASA associated with that Operator becoming insolvent, then CASA should perform the financial assessments regularly as the financial position of an organisation can be volatile. | The Australian National Audit Office (ANAO) is reviewing the requirement for Financial Viability Assessments (FVA), CASA will take further action based on the outcome of this review. | Monitor |
| 8 BIR | CASA rely heavily on a foreign operator’s AOC equivalent certificate of competency that has been issued by their State. CASA should review if there is still a valid need to examine a foreign operator’s operations and maintenance manuals. If the examination is valid, then CASA should consistently obtain and review the manuals provided prior to an initial AOC issue. If reliance is placed on the foreign AOC process, then CASA should stop obtaining the manuals, which are currently not consistently reviewed. | Note: CASA is obliged as a signatory to International Civil Aviation Organization (ICAO) to accept foreign AOC certification unless there is good reason to do otherwise. Develop policy and guidance on the criteria for the assessment of foreign operators manuals. Publish policy and guidance in CMI for the issue of foreign AOC’s. | July 2002 Jan 2003 |
| 9 CR 3 | When assessing a foreign operators application for an AOC, CASA should at a minimum obtain independent evidence that additional Australian equipment requirements have been met. We support CASA’s initiative to require that additional equipment installation certificates or receipts be provided and that the equipment installation be physically inspected during the next Surveillance audit. | Include in the CMI for the issue of foreign AOC’s guidelines and processes for this activity Amend ASSP and AOCM to include material of the above CMI. | July 2002 Jan 2003 |
| 10 BIR | The current project to review CASA internal and external delegations should seek to update the Instrument of Delegations to reflect current policy and make it easier to follow. Staff should be reminded of current delegation requirements, particularly in relation to the temporary variation of certificates. Management should consider if the delegations can be summarised in a manner similar to CASA’s financial delegations to improve ease of use. | Airline Operations Branch is progressively reviewing Delegations. Instruct staff that the General Manager Airline Operations (GMAO) will be the Delegate for the issue of AOC’s and COA’s. Consider further action to be taken following completion of the delegation review. | In progress Complete To be considered |
| 11 BIR | While, it is recognised that the GMAO has increased the role of Airline Office Managers, we recommend that their role be further extended to undertake a quality review of the documentation supporting each AOC/COA issue before approval is sought from the central office delegate. | Develop a Standard Form Recommendation (SFR) for the Airline Operations Branch. The SFR provides a mechanism for Airline Office Managers review AOC/COA recommendations to Central Office. Formalise the SFR and associated process, as part of the AOCM review. | Completed, Dec 2001 Jan 2003 |
| 13 CR 2 | Each AOC and COA file should stand-alone in providing a record of the activity relating to AOC and COA issues. All work and relevant discussions should be fully documented and support the decision ultimately made by CASA regarding the issue of an AOC or COA. A filenote template could be developed to be used to record the details of relevant activities or discussions that contributed to the decision to issue, or not issue, an AOC. | The Records Management Manual is planned for amendment. This amendment will include a standardised file structure along with improved process. Develop a filenote template as a registered form and incorporate instructions for its use in the amendment of the Records Management Manual. | September 2002 July 2002 |
| 14 CR 2 | Matters identified during AOC and COA activity which require follow-up during surveillance activity, or vice versa, must be clearly documented on both relevant files to ensure that risks identified are addressed and matters are not overlooked. CASA should look to use Pentana to schedule follow-up initiatives and flag matters. Ultimately, the systems for recording AOC/COA activity and Surveillance activity should be integrated. | Implement Pentana into the Airline Operations Branch, as an interim solution. Amend CMI on audit protocols, to provide enhanced processes for follow up and preparation of surveillance activities. Amend ASSP manual to include the content of the above CMI, as part of the ASSP manual rewrite project. Conduct feasibility study of a replacement of the ASSP Information Technology infrastructure, with an integrated solution. | Completed, Nov 2001. July 2002 Sep 2002 Dec 2002 |
| 15 CR 2 | Operational staff should be provided with guidance on administrative processes that support the AOC and COA activity. For example, guidance on documentation of work and file management is important to ensure that CASA’s entry control role is completed and documented appropriately to manage the risks associated with the function. | Amend the Records Management Manual to include a standardised file structure, along with improved process. Instruct Airline Managers to implement the administrative procedures outlined in the AOCM. Review effectiveness of implementation. | September 2002 May 2002 Dec 2002 |
| 16 BIR | AOC and COA files should be established using a standard structure designed to ensure that documents can be quickly located and that documentation is complete and support decisions made. For example, AOC and COA files could be improved by implementing the following initiatives: - A checklist in the front of the file, as is used by the International Office for Foreign Operator AOC activity is a good control to ensure that all relevant documentation is placed on file and also serves as an index for the file. - File dividers to separate documentation relating to each specific AOC or COA issue, renewal or variation. - Documentation that is likely to be referred to on a regular basis, such as AOCs, could be copied onto coloured paper as is the case in Melbourne office, to make location easier. Files should include referencing to other CASA files and to other documents on the file where there is reliance on or discussion of other activity undertaken. | Instruct Airline Office Managers to implement the protocols for audit files into the operational files. Instruct Airline Office Managers that they must enforce file protocols. Review effectiveness of implementation. | May 2002 May 2002 Jan 2003 |
| 17 BIR | We recommend that management reports be produced by each office on a monthly basis, for the benefit of the airline office Managers and the GMAO. For example, such reports could include: - AOC and COA work completed during the reporting period, that is certificates issued or varied; - Current work in progress; - A summary of any matters of significance or interest identified in the course of the work; - Scheduled work for the coming period; and Any significant finance or HR matters, including a summary of budget to actual. | Develop a weekly reporting structure – to enable communication from Airline Offices to the Senior Management Group Implement the weekly reporting structure as a part of the Divisional Communications Plan. . | July 2002 August 2002 |
| 18 BIR | Surveillance audits are generally performed on Airline Operators on a cyclical basis throughout the year. Should a surveillance audit identify any significant safety issues, it is presumed that appropriate action against the operator would be taken to minimise any risks. Accordingly, we question why an AOC could not be issued for an extended period of time, as is allowed by s27(7) of the CAA, with reliance on surveillance activity to identify any cause for grounding or suspending an AOC. | Certificates issued under the existing regulatory framework, time limited certificates will continue to be issued. For certificates issued under the new regulatory framework, the Executive Operations Committee has endorsed the use of perpetual certificates for Australian based organisations. These regulations will be subject to consultation processes. |  |