Milestones for Contracts signed as at 30 May 2001

Agreed Milestones for the Back O'Bourke Centre Limited

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six monthsFirst six monthsSecond six monthsSecond six months | CaféMature/Flood River PavilionPath between Untamed River and Mature River including BoardwalkRamp to Flood and Drought Room. | 31/08/200131/08/200101/02/200201/02/2002 |

## Agreed Milestones for the Bellingen Shire Council

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| Second six months | Completed business plan identifying patterns of usage for a community bus, leasing costs, sustainability and replacement costs. | 14/04/2002 |

Agreed Milestones for the Warrumbungle Rural Community

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months Second year Third year | Formalise lease of old Westpac Bank building; modify internal/external structure; Relocate Telecentre/WAR FM and Rural Financial Counselling Service; Advertise and employ Regional Coordinator; Tender applications requested for Mentoring Feasibility Study; Commence operations at new location. Fully equip outside broadcasting facility; 1st 6 monthly Project Report. Report on Feasibility of Mentoring Project released. 4th and 5th 6 monthly Project Report; Telecentre and WAR FM fully self funded. | 31/10/2001 30/04/2002 31/10/2002 31/10/2003 |

Agreed Milestones for the The City of Greater Lithgow Mining Museum Inc

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months Second year | Establish office facilities, develop & implement marketing plan, accounting & records management systems. Negotiate & formalise cultural heritage partnerships, catalogue museum collection & develop assets register. General business development & planning, support rail operator accreditation, establish "Grand Circular Rail Journey" with Zig Zag Railway. | 21/11/2001 21/05/2002 21/11/2002 |

Agreed Milestones for the Nimbin Neighbourhood and Information Centre Inc

| #### Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | Purchase and installion of new photocopier and computer. | 01/11/2001 |

Agreed Milestones for the Bingara Shire Council

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | Data gathering and community consultation; initial Consultant Report; Final Consultants Report. | 01/11/2001 |

Agreed Milestones for the Nambucca Shire Council

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months Third six months | Demolition of existing buildings; Begin construction of new amenities; Further progress on new construction with completion of kiosk and amenities Completion of project | 21/11/2001 21/05/2002 21/11/2002 |

Agreed Milestones for the Narrandera Pre-School Inc

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months | Completion of Architects Plans, clear site, begin construction. Building Construction | 01/11/2001 01/05/2002 |

Agreed Milestones for the Snowy River Shire Council

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months | Completion of individual town and shire wide youth forums and consultations; nomination/election of Yourth Councillors; identification of potential mentors. Identification and prioritisation of issues for tabling; establishment of mentoring networks; web page set up; feedback/evaluation strategies developed and in place. | 21/11/2001 21/05/2001 |

Agreed Milestones for the Northern Rivers Performing Arts Incorporated

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | Purchase and installation of in house audio system; Purchase of seating for auditorium and upgrade of auditorium interior lighting | 01/11/2001 |

Agreed Milestones for the Bowraville Arts Council Inc

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months First six months Second six months Second six months Second year Second year Third year | Purchase of building Confirm, seek and establish pledges of support for labour Sourcing of quotations, development application and relevent permits Employment of Project Manager Completion of foyer area Continue restoration of theatre space, fire proofing, ventilation Completion of theatre restoration, seating & ventilation | 30/10/2001 28/11/2001 28/05/2002 28/05/2002 28/11/2002 28/05/2003 28/11/2003 |

Agreed Milestones for the Nambucca District and Combined Services Museum Inc

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | A Community Plan | 19/08/2001 |

Agreed Milestones for the Uralla Shire Council

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months Second year | Meet businesses, review reports & data, set up benchmarks, establish contacts. Start preparing business plans, meet cluster contacts, work with new ventures and synergistic IT hubs, explain and promote e-commerce opportunities. Business plans completed for key businesses, cluster meetings, IT hub promoted on internet, e-commerce. Business planning commonplace, clusters established, telecommunication hub interest shown, project employee establishing broader client base. | 30/09/2001 01/04/2001 01/04/2002 |

Agreed Milestones for the Australian Cotton Exhibition Centre Ltd

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six monthsSecond six months | Construction of building and exhibits, site development.Retail & office fit out, stock, signage/promotion.. | 01/10/200101/04/2002 |

Agreed Milestones for the Snowy River Shire Council

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | Completion of community consultation; production and release of strategic plan. | 14/11/2001 |

Agreed Milestones for the Lightning Ridge Improvement and Beautification Committee

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | Lay a 2000m 1" poly waterline from the water source to the crossroads with drip feeds to each of the 600 plants. Construct a 1600m fence consisting of star pickets at 2.5m spacings with top wires. | 14/11/2001 |

Agreed Milestones for:  Tweed Economic Development Corporation Ltd.

| Period | Milestone Description | Milestone Target Date |
| --- | --- | --- |
| First six months | Expand on brief and develop terms of reference and invite proposals | 30/06/2001 |
|  | Review proposals and appoint consultant(s) |  |
|  | Consultancy Stage One - Review |  |
|  | Consultancy State Two – Information |  |
| Second six months | Consultancy Stage Three - Outcomes | 31/12/2001 |
|  | Project Review |  |

Agreed Milestones for the Ramingining Community Council Inc

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | Purchase and installation of equipment: HP Colour Laserjet 4500DN printer, Adobe Publishing Collection software, Kodak DC4800 Digital camera & software. | 01/11/2001 |

Agreed Milestones for:  Northern Territory Christian Schools Association

Period			Milestone Description			  Milestone Target Date

#### First six months

*  Select Community Development Trainee		30/06/2001

Officers

*  Enrol Trainee Officers at the Northern		30/06/2001

Territory University

#### *  Document community core-beliefs and 		30/06/2001

values

*  Conduct community meetings to distil 		30/06/2001

#### vision and mission

*  Identify possible community development		30/06/2001

projects

#### Second six months

*  Develop individual project profiles		31/12/2001

*  Conduct critical path analysis				31/12/2001

#### *  Draft Community Development Plan			31/12/2001

*  Consult community for Community Development		31/12/2001

Plan modification

*  Submit final Community Development Plan		31/12/2001

*  Complete Northern Territory University course		31/12/2001

- Agreed Milestones for:  Austrade – Delivery of TradeStart services to by Northern Territory Chamber of Commerce and Industry to Central Australia

Period			Milestone Description		  Milestone Target Date

First twelve months

Promote the TradeStart program and the availability of services		30/12/2001

under this joint project approach

Promote exporting within the local business community to			30/12/2001

encourage the maximum number of capable companies to export

Provide leadership and local education on the benefits of trade		30/12/2001

and international relations to local communities and business

Act as in-region contact person for Austrade services and other30/12/2001

export assistance services

Assess export readiness of potential exporters and counsel them accordingly												30/12/2001

Refer non-export ready clients to other services				30/12/2001

Provide advice to potential exporters on how to start exporting		30/12/2001

Provide Austrade’s readily available information about			30/12/2001

international markets

Provide information on available financial support				30/12/2001

Provide feedback to Austrade on regional business and program performance												30/12/2001

Second twelve months

Promote the TradeStart program and the availability of services		30/12/2002

under this joint project approach

Promote exporting within the local business community to			30/12/2002

encourage the maximum number of capable companies to export

Provide leadership and local education on the benefits of trade		30/12/2002

and international relations to local communities and business

Act as in-region contact person for Austrade services and other		30/12/2002

export assistance services

Assess export readiness of potential exporters and counsel them		30/12/2002

accordingly

Refer non-export ready clients to other services				30/12/2002

Provide advice to potential exporters on how to start exporting		30/12/2002

Provide Austrade’s readily available information about			30/12/2002

international markets

Provide information on available financial support				30/12/2002

Provide feedback to Austrade on regional business and program		30/12/2002

performance

Agreed Milestones for the Jones Hill State School

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months First six months | Construct poultry area, aquaculture shed, hydroponic system, pond and fences, provide water, power, raised garden beds and pine tree removal and milling. Students, parents and community participation in food production. | 31/08/2001 31/08/2001 |

Agreed Milestones for the Aramac Shire Council

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| Second six months | Completed Business Plan. | 19/02/2001 |

Agreed Milestones for the Lake Eyre Basin Coordinating Group

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six monthsSecond six months | Partners and contribution confirmed; project planning and management arrangements set up, facilitator/s appointed and work plan prepared to satisfaction, instigation meetings held; data gathering and issues identification underway.Regional action plan prepared and finalised; marketing and community development plans prepared; guide for the development of small business plans; other guides and training as identified | 19/08/200118/02/2002 |

Agreed Milestones for the Barcaldine Shire Council

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months | Complete selection of consultants to undertake research on project phases. Review of overall project, final project reporting, financial acquittals and auditing. | 01/11/2001 01/05/2002 |

Agreed Milestones for the Aramac Shire Council

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months | Selection of Consultant to undertake research on project phases, implementation planning, development of action plans. Final reporting of all stages of project research and presentation of final report to key stake-holders. | 01/11/2001 01/05/2002 |

Agreed Milestones for the Longreach Cultural Association Inc.

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | Completion of repair work and painting, both upstairs section and downstairs ceilings | 01/11/2001 |

Agreed Milestones for the Longreach Shire Council

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months | Architectural building design & supervision, council approval, commencement of building construction Completion of building construction. | 07/11/2001 07/05/2002 |

Agreed Milestones for the Queensland Macropod and Wild Game Harvester Association

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months Second year | Establish contacts and networks; Identify capacity building requirements of members; Initiate supply chain management training for harvesters; Establish website and promotional material; Evaluation training package progress. Develop work plan for Dec 2001-Dec 2002; Hold first capacity building training session; Hold first industry forum; Continue work on Supply Chain Management, Rural Leadership Training, forums, website development, capacity building, training package adoption, data bases, promotional support and communication strategies in line with new work plan. | 31/10/2001 30/04/2002 30/04/2003 |

Agreed Milestones for the Ecofish TNQ Ltd

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months Second year Second year | Employ a full time Executive Officer; complete a strategic plan. Implementation of actions identified in Strategic Plan Implementation of actions identified in Strategic Plan Implementation of actions identified in Strategic Plan | 07/11/2001 07/05/2002 07/11/2002 07/05/2003 |

Agreed Milestones for the Bloomfield Local Arts Council

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months | Purchase of Computer, photocopier, printer, scanner & software, paper. Advertise and employ part time staff. Evaluate and review marketing strategies, content layout, etc. Ongoing skills development for staff and volunteers. TBVN to be self-funding. | 01/11/2001 01/05/2002 |

Agreed Milestones for the Darling Downs Vision2000 Assoc. Inc

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months Second year Second year | Strategic Planning - development of DDV2000 operation plans, legal and structural issues and water user financing scenarios; People Resources - coordination, planning and communication; environmental impact of effluent irrigation on the Downs and Murray Darling System Identify and quantify socio-economic and environmental benefits;project coordination, business plan monitoring and communication; review capital and operating costs; development of financial models, project coordination, communication, planning. Development of Operating Model, investment marketing, contractual and institutional arrangements; financial management, advisory entity; project coordination, communication and planning. Project coordination, communication and planning required to complete the process and confirm relationships between water users and other parties | 07/11/2001 07/05/2002 07/11/2002 07/05/2003 |

Agreed Milestones for the Bowen Tourism & Regional Development Bureau

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months | Employ and train IT technician, purchase computer software, research information for website Complete training for IT technician; design, develop, test and upload website; prepare final report on project | 07/11/2001 7/05/2002 |

Agreed Milestones for:  Border Highlands Rail Company Pty Ltd

Period			Milestone Description			  Milestone Target Date

First three months

*  Review of design documentation			15/03/2001

*  Construction and fit out tenders			15/03/2001

#### *  Commence construction and fit out		15/03/2001

Second three months

*   Continue construction and fit out				15/06/2001

*   External works						15/06/2001

# Last six months

*   Completion and final approvals				21/12/2001

# Agreed Milestones for:  Northern Areas Council

Period			Milestone Description		  Milestone Target Date

First six months

*   Rehabilitation equipment				30/07/2001

*   Site preparation					30/07/2001

*   Building construction				30/07/2001

*   Pool installation					30/07/2001

Second six months

*   Building fit out					31/01/2002

*   Pool fit out						31/01/2002

*   Completion						31/01/2002

Agreed Milestones for the Coober Pedy Times Association

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | Staff to solicit advertising revenue from regional towns, payment for articles, travel to each town to appoint part time workers/obtain advertising revenue. Obtain brochures.. | 12/08/2001 |

Agreed Milestones for the Kangaroo Island Development Board

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | Update the Kangaroo Island Strategic Plan, and identify business opportunities to be promoted by the Kangaroo Island Development Board | 01/11/2001 |

Agreed Milestones for the District Council of Le Hunte

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months | Completion of Polda-Wudinna 7.5 km pipeline; Completion of Town Distribution Network, Completion of Stormwater Network | 01/11/2001 01/05/2002 |

Agreed Milestones for the Mount Horrocks Historical Society Inc

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | Development of strategic plan and marketing strategy | 19/08/2001 |

Agreed Milestones for the Adelaide Hills Regional Development Board Inc

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | Completion of Financial Feasibility Study for the proposed Adelaide Hills Regional Performing Arts, Entertainment and Convention Centre. | 14/11/2001 |

Agreed Milestones for the Zeehan Neighbourhood Centre

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months | Completion of work on visitor information stop area, fence line, chairs/seats, corner hill on Main Street, school and medical centre Completion of work on Coszee, Howard's Park, Gaiety, Frank Long Memorial Park, Bus Shelters and vacant block on Main Street. | 14/10/2001 14/04/2002 |

Agreed Milestones for the Ouse Online Community Access Centre Inc

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months | Municipality literature review; development of, and undertaking of survey; resource analysis of geological/environmental factors Collation and review of all information collected; development of skill database and job matching service; development of resource database; development of business database and networks (electronic format) and website | 07/11/2001 07/05/2002 |

# Agreed Milestones for the Gippsland Development Ltd

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second year Third year | Research into cluster methodologies; Identification & engagement of target industries/firms. Development of action agendas to underpin cluster agendas Ongoing liaison; Engagement of influential Australians and overseas expertise; Benchmarking studies & liaison with cluster agendas elsewhere | 30/10/2001 30/04/2002 30/10/2002 31/03/2003 |

Agreed Milestones for the Riding for the Disabled Association of Victoria Inc

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months First six months First six months First six months First six months | Develop final report and plan with activities, milestones, costings and targets. Members workshop to provide input and further develop options Consultant to research options Meeting of consultant with committee Appoint consultant | 31/08/2001 31/08/2001 31/08/2001 31/08/2001 31/08/2001 |

Agreed Milestones for the Golden Plains Shire Council

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | The project will assist with the implementation of community plans for those five communities assisted in Stage 1 to undertake community planning; and assist a further 6 communities to undertake a community planning process and commence implementation. | 14/10/2001 |

Agreed Milestones for the Wellington Shire Council

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | completion of business plan, and launch of investment prospectus | 01/11/2001 |

Agreed Milestones for the Portland Cable Trams Inc

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First three monthsSecond three months | Finalise tenders for tram truck construction and depot construction. Depot construction commenced, Tramway construction material, 1/3 of construction labour.Completion of construction phase, testing of track. | 26/05/200128/08/2001 |

Agreed Milestones for the Warrnambool City Council

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months Second year | Appoint project management team, finalise design and obtain necessary permits Start building work on Foyer Complete work on access and reamping design for visitors; construction of theaterette and seating; mechanical arm movement assessment and construction;, hydraulic design and control engine installation;, berthing arrangements; modelling of water surface tension and movements; and lighting, safety assessment and installation. | 07/11/2001 07/05/2002 07/05/2003 |

Agreed Milestones for the Watchem Development Association

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | Purchase of a photocopier (Canon GP 225) for use by the Watchem Progress Association to produce a community newsletter | 07/11/2001 |

Agreed Milestones for:  Shire of Ravensthorpe

Period			Milestone Description	  Milestone Target Date

First six months

*  Complete building so doors can open			30/07/2001

Connect services:  toilet and changeroom

facilities, door, stairs, ceilings, rendering,

mechanical ventilation, install mezzanine

flooring, construct kiosk on mezzanine.

*   Offer sporting activities to the community.		30/07/2001

Second six months

*   Install sports floor.						31/01/2002

*   Offer increased number of sporting activities		31/01/2002

to the community.

Agreed Milestones for the Bakers Hill Business Association

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| Second six months | Completion of Strategic Plan | 01/05/2002 |

Agreed Milestones for the Shire of Dowerin

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | Engage consultants and conduct a feasibility study into accommodation Stage 1 Market Assessment Stage 2 Site/s evaluation and design Stage 3 Business Plan | 14/10/2001 |

Agreed Milestones for the Bland Shire Council

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months | Construction of Visitor Information and Heritage Centre Completion of construction and fitout of Visitor Information and Heritage Centre | 01/12/2001 01/06/2002 |

Agreed Milestones for the Shire of Donnybrook - Balingup

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months | Completion of initial round of community workshops, research, networking and draft strategy production; Adoption of strategy by community stakeholders and Council; Launch of strategy document. | 14/11/2001 |

Agreed Milestones for the Shire of Kulin

| Milestone Period | Milestone | Milestone Date |
| --- | --- | --- |
| First six months Second six months Second year | Employ a Community and Services Development Coordinator (CSDC) Progress towards fostering and assisting economic development within the Kulin Shire by working with and supporting town and rural businesses Completion of term of Community and Services Development Coordinator (CSDC) | 30/09/2001 14/05/2002 14/05/2003 |

- Agreed Milestones for:  Austrade – Delivery of TradeStart services to the Kimberley Region

Milestone Description					  Milestone Target Date

First twelve months

Promote the TradeStart program and the availability of services		30/12/2001

under this joint project approach

Promote exporting within the local business community to			30/12/2001

encourage the maximum number of capable companies to export

Provide leadership and local education on the benefits of trade		30/12/2001

and international relations to local communities and business

Act as in-region contact person for Austrade services and other		30/12/2001

export assistance services

Assess export readiness of potential exporters and counsel them		30/12/2001

accordingly

Refer non-export ready clients to other services				30/12/2001

Provide advice to potential exporters on how to start exporting		30/12/2001

Provide Austrade’s readily available information about			30/12/2001     international markets

Provide information on available financial support				30/12/2001

Provide feedback to Austrade on regional business and program		30/12/2001

performance

Second twelve months

Promote the TradeStart program and the availability of services		30/12/2002

under this joint project approach

Promote exporting within the local business community to			30/12/2002

encourage the maximum number of capable companies to export

Provide leadership and local education on the benefits of trade		30/12/2002

and international relations to local communities and business

Act as in-region contact person for Austrade services and other		30/12/2002

export assistance services

Assess export readiness of potential exporters and counsel them		30/12/2002

accordingly

Refer non-export ready clients to other services				30/12/2002

Provide advice to potential exporters on how to start exporting		30/12/2002

Provide Austrade’s readily available information about			30/12/2002

international markets

Provide information on available financial support				30/12/2002

Provide feedback to Austrade on regional business and program		30/12/2002

performance

- Agreed Milestones for:  Austrade – Delivery of TradeStart services to the Gascoyne Region

Milestone Description				  Milestone Target Date

First twelve months

Promote the TradeStart program and the availability of services	30/12/2001

under this joint project approach

Promote exporting within the local business community to		30/12/2001

encourage the maximum number of capable companies to export

Provide leadership and local education on the benefits of trade	30/12/2001

and international relations to local communities and business

Act as in-region contact person for Austrade services and other	30/12/2001

export assistance services

Assess export readiness of potential exporters and counsel them	30/12/2001

accordingly

Refer non-export ready clients to other services			30/12/2001

Provide advice to potential exporters on how to start exporting	30/12/2001

Provide Austrade’s readily available information about		30/12/2001

international markets

Provide information on available financial support			30/12/2001

Provide feedback to Austrade on regional business and program	30/12/2001

performance

Second twelve months

Promote the TradeStart program and the availability of services	30/12/2002

under this joint project approach

Promote exporting within the local business community to		30/12/2002

encourage the maximum number of capable companies to export

Provide leadership and local education on the benefits of trade	30/12/2002

and international relations to local communities and business

Act as in-region contact person for Austrade services and other	30/12/2002

export assistance services

Assess export readiness of potential exporters and counsel them	30/12/2002

accordingly

Refer non-export ready clients to other services			30/12/2002

Provide advice to potential exporters on how to start exporting	30/12/2002

Provide Austrade’s readily available information about		30/12/2002

international markets

Provide information on available financial support			30/12/2002

Provide feedback to Austrade on regional business and program	30/12/2002

Performance