13th June 2003

M30346:DGG:dgg

Hon Senator Peter Cook  MP

Chairman

Foreign Affairs, Defence and Trade Committee

S1.57

Parliament House

CANBERRA   ACT   2600

AUSTRALIA

Dear Senator Cook

ROYAL PNG CONSTABULARY DEVELOPMENT PROJECT

Thank you for the opportunity to meet in Mount Hagen at the Chamber of Commerce luncheon, and thereafter, at Mount Hagen General Hospital. I trust that the brief visit by the Senate Team to PNG has been useful and will result in a better understanding of the problems and issues pertaining to this country.

Whilst at the Chamber of Commerce lunch, I was discussing my concerns in relation to the direction of the Police Programme in PNG with Senator MacDonald. I confirm my belief that this project has fundamental issues restricting its success that need to be addressed as a priority. I was asked to prepare a brief in relation to this matter and now enclose same for your attention.

I would be pleased to answer any enquiries or provide further information if needed. Please also feel free to contact me should you require further details or information with regards to Mount Hagen General.

Yours faithfully

GUINN PKF

DG GUINN  OBE

PRINCIPAL

Mount Hagen office

Encl.

cc.   Australian High Commission

Port Moresby

Ms Saxon Patience

Senior Research Officer – FA,D&T Committee

BRIEF TO THE SENATE FOREIGN AFFAIRS, DEFENCE

AND TRADE COMMITTEE

ROYAL PNG CONSTABULARY DEVELOPMENT PROJECT

RECOMMENDATIONS FOR STRATEGIC IMPROVEMENT

# Introduction

The Australian Government, through its international aid agency AusAID, has been assisting the Royal Papua New Guinea Constabulary (RPNGC) through the institutional strengthening programme known as the Royal Papua New Guinea Constabulary Development Project. This Project has been in operation for more than 13 years in its current and previous phases. The Project consists, essentially, of the provision of technical advisors from various spheres of policing background to the RPNGC. In principle, it is similar to a number of other AusAID-funded projects in Papua New Guinea, where advisors have also been provided to assist with the strengthening of those respective institutions. To date, in excess of AUD180 million has been spent assisting the RPNGC.

# The Issues

A safe and reasonably law-abiding environment is required by any society to provide the basis for the protection of its population, the promotion of business in the economy and the encouragement of investment from abroad. Law and order issues are therefore key to all sectors of business and the community.

The Project commenced in the late 1980’s as part of the move by the Australian Government away from budgetary assistance to PNG, in favour of project aid. Strengthening of the RPNGC in post-Independence Papua New Guinea was seen as a National priority, and received assistance accordingly.

Unfortunately, the project has not been successful, with the RPNGC arguably being in a worse condition now than it was at the time of its commencement. It is difficult to identify any aspects of the Project where sustainable improvements have been achieved. This is not to say that the Project has been the cause of the decline in the Police Force, but rather, the decline has occurred in spite of it.

The key question to ask, then, is “why has the RPNGC Development Project failed to produce the intended outcomes?”

The current Project acknowledged that the current RPNGC can be improved through operational and management training. However, the delivery of the training process is fundamentally flawed, to the extent, that very few if any of the anticipated outcomes have been achieved over the past 13 + years.

The thrust of the current and the former incarnations of the Project have been based on the concept of providing advisors to the Force. These advisors are purely that – they may (and do) provide advice, but have no rank and no authority within the Force. In other words, the approach has been the same for the Police in principle as is the case for health, education and other civilian projects.

This, I believe, was doomed to fail ab initio. It is a fact of life in any disciplined force anywhere that the system works through a culture of “pips and stripes”. I do not believe that advisors to the Constabulary (as, indeed, with any disciplined force) should be engaged on the same basis as educationalists or health specialists. They cannot perform the duties required of them within the RPNGC without the authority of the their positions.

This is not meant to be a criticism of the advisors who have been engaged by the Project, as their hands have been tied by the terms of reference of the Project.

# Recommendations

As noted above, it is believed that the Project is fundamentally flawed in its approach to the issue of strengthening the RPNGC. If the project is to have any chance of succeeding, a new strategic direction is required.

The central tenet of this proposal is that contract officers be engaged by the RPNGC to assist with day-to-day duties. These policemen should be employed as line officers and primarily hold middle management ranks, of say sergeant to inspector. Positions at these levels would allow direct interfacing with the rank and file and would mean that the officers would be more hands-on. Higher ranks could be considered for specific purposes, but would need to be in consultation with the Papua New Guinea Government and the RPNGC, as serious resistance may be encountered should the current higher ranking officers feel that their positions were being challenged.

The employment of the contract officers should be handled completely by the RPNGC. In other words, the Constabulary would decide on the positions required (perhaps a degree of consultation could be provided here), would advertise the positions, would interview and finally recruit the contract officers. The role of AusAID would be (as mentioned, to possibly provide some assistance in identifying the positions requiring filling,) the funding of the recruitment process and ongoing cost of the officers whilst on duty in Papua New Guinea. In this way, PNG would have ownership over the recruited officers and any arguments of the sovereignty issue would be null and void.

(NB. Should the sovereignty concern no longer be the issue that it has been in the past, the Australian Government may wish to have more say in the recruitment, and thereafter, the operational process.)

A further issue that needs to be addressed is the concern that the Australian Government and AusAID may have in relation to the perceived danger for Australian officers to be recruited. However, with the recommended scenario, this is not really an Australian issue as PNG will have effective ownership over the recruitment process. Furthermore, advertisements should not be restricted to Australia. Indeed, the RPNGC should advertise and recruit from throughout the Commonwealth. (The argument for restricting the positions to Commonwealth countries, however, is that the underlying legal systems in each country are in most cases similar.) It is important, however, that all appointments should be made on a merit basis.

By taking this approach, applicants Commonwealth-wide would be making their own assessments of the danger issues as well as any other factors. Australia (through AusAID) would not be placing its own personnel in “dangerous” occupations with the issues that attach to such decisions.

Moreover, not all contract positions would be in the “firing line”. A number of positions throughout the country would be needed in such areas as administration, CID, fraud, prosecutions, etc.

Another issue may be the concern by some Papua New Guinea National Policemen that their promotional prospects may suffer as a result of the introduction of overseas contract officers. To allay this fear, a condition of the contracts could be that the positions would be non-promotional, ie sideways positions. This should diffuse possible complaints by PNG officers concerned that their promotional prospects may be prejudiced.

(I would note here for the record that I am not saying that a role does not exist for specialists in an advisory capacity to the Constabulary. However, as a generalisation, these should be restricted to the more formal educational issues, ie teaching in a classroom environment. These advisors would generally be dealing with longer term training issues, whereas the contract officers would be dealing with “today’s” problems.)

A variation on a theme would be the establishment of a twinning project between the RPNGC and one or more of the various police services in Australia. This could be run as part of the programme, where PNG police staff would be sent to Australia for 1-2-3 years with the respective equivalent officers being transferred to PNG for the same period. If AusAID were to be concerned with danger issues with such an arrangement, perhaps these positions could be restricted to non-confrontational areas – fraud, CID, investigations, etc. However, police at both ends should be commissioned for the period that they would be respectively overseas. In terms of the training of the PNG staff, this would be a medium term programme, not immediate. However, the Australian counterparts’ roles in PNG would have immediate impact.

Naturally, the Australian Government, in conjunction with the PNG Government, would need to determine a set of required outcomes from the redesigned Project (just as it has expected outcomes from the existing Project). The difference would be that the redesigned Project would have a chance of achieving sustainable outcomes, whereas currently, this is not the case.

It may be claimed that these recommendations over-simplify the issues and that other complexities have not been addressed. It is acknowledged that the RPNGC has many other problems (including poor housing, lack of equipment and other resources, etc). However, the personnel management issue is fundamental to the success of any attempt to improve the operations of the Force. To not address this issue is to sentence the Constabulary to more of the same.

# Benefits

A number of benefits will flow from the recommendations. These can be summarised as follows:

  - Contract officers will have the authority to back up recommendations and be able to make line decisions, resulting in immediate action;

  - Immediate results would be expected to be seen as contract officers would be dealing with day-to-day (current) matters, not necessarily issues that will not come to fruition for months or years;

  - Contract officers will be able to conduct on-the-job training in the field and in their respective sections;

  - Many of the newer/younger/lower ranks within the RPNGC are looking for direction and leadership, but currently, are not receiving it. They then fall into the bad habits that already pervade the Force due to the current culture that exists. This initiative will help to reverse that trend (from the front);

  - Contract officers would be from overseas, and therefore, outside of the wantok system. This would help to provide a break in the cycle in relation to the current culture that exists in the Constabulary;

  - The general public would be supportive because they would see a workable policy being implemented in the Constabulary. They are fully aware of the wantok pressures that exist within the Force, and indeed, use the system to their own advantage where possible. However, I believe that often the wantok system is invoked by people because they cannot obtain a service in the ordinary course of events. The majority of Papua New Guineans would prefer to see an efficient and effective service without the nepotism.

  - Many of the older people in the population talk of the Administration days when the kiap system operated very effectively. The people knew that those who disobeyed the laws of the land would be caught and punished, people could move freely without fear for their safety – the system worked because, apart from other reasons, the majority of kiaps were from outside of PNG (especially in the earlier years) and therefore outside of the social system that exists in PNG. I note this not from any suggestion to return to the Administration days – PNG is a sovereign nation as it should be. Rather, it is mentioned in terms of the belief that the people in general would welcome the influx of contract officer policemen in Port Moresby and throughout the Provinces, to assist with the current problems. The majority of the population would not resist the programme. Rather, the only resistance contemplated would come from those members of the Force who have a vested interest in maintaining the chaos that currently exists – due to either their desire to continue their unlawful activities or their fear of having to perform. However, I believe that such officers would be in the minority and the vast majority of the men and women in the Force would welcome the support;

  - Many police are disenchanted with the corruption, slackness and other problems within the Force. They would support this initiative;

  - Many police are not happy with the perception that the general public has of them. They will support an initiative that will have the effect (amongst other issues) of improving the image of the Force;

  - An improved Police Force will result in less law and order problems, as culprits and potential offenders will be more likely to think twice before committing unlawful acts;

  - The general population will be happier over time with the improvement in law and order;

  - An improved law and order situation will result, ultimately, in additional investment by business as confidence is restored;

  - Likewise, overseas investment will in time increase as the perception of a safer business environment improves;

  - The Australian electorate is becoming more critical of the amount of aid to, and usage thereof by, Papua New Guinea. Positive results in terms of an improvement in law and order within PNG would be supported by the Australian people;

  - PNG is being increasingly seen as a security risk in the region as its internal grip on law and order continues to weaken. Positive results from the recommended change of strategy would help to reduce this risk – both in actual terms and by perception.

# Precedent

During the 1980’s, fifty (50) contract policemen were recruited from the United Kingdom. They signed contracts with the PNG Government and were in the process of preparing to travel to Papua New Guinea when a change of Government in Port Moresby occurred. The contracts were cancelled by the incoming Government at that time and PNG was forced to pay compensation to the various officers for breach of contract.

(NB. I believe that in 2003 more than 50 officers would need to be recruited. An assessment would need to be made by the PNG and Australian Governments of the number of policemen required, with input from the RPNGC.)

# Criticisms

During the currency of the Police Project a number of assessment teams from Canberra and the High Commission have toured PNG to determine the effectiveness (or otherwise) of the Project. Most of the above issues have been raised by the Western Highlands Chamber of Commerce & Industry and by various individuals in the past, but previously to no avail. In defence of these teams the suggestions for improvement were outside of the general terms of reference of the Project. However, sometimes it is important to think outside of the square.

To date, the Police Project has been an abject failure with little, if any, sustainable improvement in the Constabulary. Indeed, as argued earlier, the Police Service has been in decline over the past 13 + years. I am firmly of the view that a radical (ie, radical in terms of divergence from the current and previous policy, not necessarily in concept) refocusing of the Project is the only course of action that will produce any of the desired outcomes.

Issues that have been raised in the past (and I am sure will be raised again) in relation to the above suggested change in strategic direction have been summarised below, together with responses to those criticisms.

| Predicted Criticisms |  | Responses |
| --- | --- | --- |
| - The Sovereignty Issue Often in the past, the issue of sovereignty has been raised. The argument follows that Australia cannot appoint or impose Australian police on the Government of Papua New Guinea. The Government of PNG should rightly complain about/refuse such a project. - The Advisor Issue The issue here is that the strategic direction of most of Australia’s overseas strengthening projects is on the basis of providing advisors only and not line officers. The intention is to train personnel from the country receiving the support (in this case, PNG) and leave a sustainable resource once the project has been completed. - The Danger Issue This argument states that it is not the policy of the Australian Government and, therefore, AusAID to place personnel in dangerous postings or circumstances (excluding military postings). - The Police Hierarchy Issue It has been argued that the RPNGC would react negatively to a project where contract officers were to be introduced, particularly at senior ranks, if officers were to be contracted at that level. - The Promotional Issue It has further been argued that the rank and file would resent the introduction of contract officers in that it could be perceived that this would impact negatively on their promotional prospects. |  | - The Sovereignty Issue It is not believed that a sovereignty issue exists for the following reasons: - RPNGC would have ownership over the recruitment process, in that it would advertise, interview and select the contract officers; - Under the suggested scenario, the contract positions should be advertised throughout the Commonwealth to allow access to a larger pool of expertise. This would also have the benefit of further diminishing any risk of accusations being made to the effect that Australia would be imposing its views/plans on PNG. However, all appointments should be merit-based; - Australia (AusAID) would fund the cost of the recruitment and ongoing costs of the officers; - From a practical viewpoint, the contract officers would be “employed” by PNG on the same basis as for contract officers in other sectors of the bureaucracy, except that they would have the authority of their respective ranks. - The Advisor Issue Whilst not disputing the intended outcome of leaving a sustainable resource after project completion, it needs to be understood that the culture in the disciplined forces is different to that which exists in the civilian world. Disciplined forces worldwide operate on a culture of “pips and stripes”, ie of giving and receiving orders. The current programme of providing advisors without rank (and, therefore, without authority) to the RPNGC was doomed to failure from the beginning. This is not to say that a role does not exist for advisors in purely teaching capacities, but real assistance is required in the form of duty officers in most if not all operational facets of the Constabulary. These officers must have the authority to command their respective operational staff to be effective. On-the-job training would take place as a component of the command process. - The Danger Issue By the RPNGC having ownership over the recruitment of contract officers (as opposed to AusAID providing same) the assessment of the risk of the assignment becomes one for the applicants to make. Furthermore, not all contract positions would be “front-line” in terms of being exposed to operational dangers. Whilst officers would need to be spread throughout the country to be effective, roles such as administration, CID, fraud, prosecutions, etc would be mostly non-confrontational. - The Police Hierarchy Issue To be truly effective, the real need from an operational viewpoint is at middle management level. Recruiting contract officers to the ranks of sergeant to inspector would provide experienced personnel at an effective level within the force. These positions would be “hands-on”, where the contract officers would be providing direction and guidance (and on-the-job training) to the rank and file of the Constabulary within their respective vocations. It is acknowledged that providing officers at senior levels could be a sensitive issue. - The Promotional Issue On the contrary, many young police men and women are looking for positive leadership and guidance, but are not receiving same. Most of the personnel who may object would be likely to be those with vested interests in continuing the chaos, ie those manipulating the system and/or those not wishing to work. However, for those genuinely concerned about their promotional prospects, the matter can be very easily dealt with by making all contract officer positions non-promotional, ie additional or side-ways positions. By adopting this approach, the existing middle management of the Force with such concerns (and those hoping to achieve those ranks) should have their fears allayed. |

# Conclusion

Law and order issues are of concern to all living within PNG, from the village man to the business sector to our leaders. Presently, these concerns appear to be growing.

In the larger picture, PNG is the largest of the South-West Pacific Nations (excluding Australia and New Zealand), both in terms of geographic size and population. A destabilised Papua New Guinea would not only be a problem for itself, but potentially, for the region. For this reason alone, an effective solution to the strengthening of the RPNGC is essential.

By all counts, the Royal PNG Constabulary Development Project has been an abject failure. Very few, if any, of the anticipated outcomes have been achieved during the life of the Project (in its current and previous phases).

As the previous approach has not been successful, consideration must be given to other strategies (ie, possible remedies that fit outside of the square). It is realised that the recommendations contained herein are a quantum leap from the current direction of the Project, but a significant change is required as the current Project (and its previous incarnations) have failed to date.

I believe that the arguments espoused above are credible and workable, and should be considered as part of the approach to resolving the current problems that exist with in the PNG Police Force.

DG GUINN  OBE

MOUNT HAGEN