- RISK MANAGEMENT STRATEGIES

| POTENTIAL RISK AREA | #### RISK MANAGEMENT STRATEGIES EMPLOYED |
| --- | --- |
| Market congestion | - OASITO closely monitored the market, liaised with major players and actively sought out new players. - OASITO maintained an open door policy for industry. - Release of tenders to the market was staged. |
| Comparison of agency costs and vendor prices | - A set of financial models were developed to capture and project relevant Agency costs associated with the performance of the tendered services, and to compare those costs with tendered prices. - OASITO provided Agencies with a cost model proforma and methodology to assist Agencies populate cost models with data and access to financial consultants to assist in development of their model. - The SOW and Service Level Schedules were reconciled against Agency cost baselines by independent experts. - The financial evaluation model and methodology was comprehensive to accommodate all foreseeable costs under the outsourcing scenario and attempted to ensure that the comparison of internal costs and tendered prices was fair. - The financial evaluations were very thorough with potential hidden costs identified and included. There was a high degree of collaboration between the financial and technical teams to ensure that any elements missing from a tenderer’s proposed solution (eg missing software, hardware, telecommunications links, or staff) were captured and costed. |
| Service level specification | - Agencies were requested to measure existing service levels prior to specifying tender requirements through use of historical data. - Agencies prepared the Service Level Schedule and OASITO assisted Agencies in establishing service levels by providing: - a Service Level Guide, including a Service Level template to provide a starting point; - reference points such as Gartner Group “industry standard” and “best practice” levels; - workshops to facilitate a transfer of knowledge from previous outsourcing contracts, including lessons learned; and - expert advice to ensure technical service levels are described in a contractually enforceable manner - The Service Level Schedule identified, defined and set metrics for service level measures and set out a service credit regime to apply where service levels are not met. - OASITO assisted Agencies negotiate an agreed Service Level Schedule and calculation of service credits with the vendor as part of the negotiation process. ## Ongoing management of service levels is between Agencies and the Contractor. |
| HR management | - OASITO Guides (including HR Kit) reflected the Government preference for, and recommended for business continuity reasons, that Agencies adopt ‘Phased’ employee transition arrangements to maximise access to staff corporate knowledge in the transition phase. However the choice of approach was made by Agencies. All Agencies chose the Clean Break approach. - Agencies employed a number of strategies to retain key staff in the lead up to outsourcing. - The Guides encouraged Agencies to ensure they have access to appropriate skill sets post handover including IT strategic planning skills, contract management skills, pricing and technical analysis skills. - OASITO HR Kit assisted Agencies manage other staff change management issues by providing HRM checklists and sharing lessons learnt. |
| Contract management skills. | - OASITO Guides encouraged Agencies to identify key contract management staff early in the tendering process and give them central roles in the evaluation and negotiation process to develop their understanding of the objectives and/or complexities of the outsourcing relationship. - Agencies were closely involved in evaluating and negotiating the final Services Agreement and by the time of contract signature, key agency personnel had an intimate knowledge of all aspects of the Agreement. - Agencies brought in specialist expertise as required. |
| Commonwealth accountability and privacy obligations. | - OASITO provided Agencies with a proforma RFT that was developed progressively over transactions and incorporated lessons learned. - Considerable expertise was brought together from both OASITO and Agencies to ensure service responsibilities were clearly delineated and accountability allocated for various functions associated with IT infrastructure services. - The terms and conditions of the Services Agreement were founded on composite Commonwealth and expert adviser knowledge and contain extensive legal protections to manage Commonwealth risk and mitigate liability. - OASITO engaged legal counsel to review the RFT to ensure it was correctly drafted and appropriate disclaimers are included. - The Contractor is required to comply with the Privacy Act, and any other similar legislation that may be enacted. The Services Agreement imposes strict requirements on the Contractor, its subcontractors and personnel regarding confidentiality, privacy and data security. A failure to comply with any of these provisions may constitute a material breach entitling the Group to terminate the Services Agreement. - The standard Services Agreement contains provisions allowing Group Agency audit representatives - including the Auditor-General or the delegate of the Auditor-General - to access all premises, personnel (including subcontractors), equipment, software, data, records and systems relating to the services in order to perform any statutory audit functions or in order to audit the Contractor's compliance with the Services Agreement. - The standard Services Agreement allows for the disclosure of any confidential information by a Group Agency required by law including to any other Commonwealth Agency, the Parliament and the Auditor-General. |
| Security | - Security was specifically addressed from both organisational and technical aspects during RFT development and the evaluation process and DSD advised on technical security aspects of the evaluation. - Agency IT security areas assessed security elements of the proposed solutions. - The Services Agreement provides that the Contractor must develop a Security Plan that complies with all Commonwealth security policies (such as Protective Security Manual and DSD ASCI 33 etc) and with Agencies’ security regimes. - The Procedures Manual (a requirement of the RFT that is developed by the Contractor and agreed by Agencies during transition) sets out in detail the security processes to be followed. - The Services Agreement provides Agencies with extensive audit rights to review the data protection procedures of the Contractor during the term. |
| Statement of Work | - OASITO assisted Agencies ensure that the RFT defines clearly and in reasonable detail the scope of services, service levels and improvement targets that must be achieved. - OASITO encouraged Agencies to have access to all necessary expertise in terms of drafting their service requirements in a way that providers can understand and relate to. OASITO provided drafting assistance. - The Services Agreement established clear mechanisms for monitoring and assessing performance. - The Services Agreement contained clauses designed to minimise the Contractor’s ability to argue for additional charges as compensation for peripheral activities that should be included in the base scope of services. - The Services Agreement ensured that fixed unit prices are achieved and that Services provided can increase by 100% over forecast volumes without unit price variation. - Tenderers must reflect anticipated price/performance improvements and efficiencies in their pricing. - The Pricing Schedule was structured to ensure pricing certainty and provides a very precise definition of what’s included in the pricing (ie clear understandings of what prices are to be charged, how they are to be charged, and how any price changes will be calculated). - The Services Agreement established mechanisms to protect the Commonwealth from excessive charging for unforeseen events, including: - the right to source any equipment or services from a third party by any means; - the right to exclude the Contractor from any competitive process for new/ additional work; - independent cost and quality benchmarking; and - a set of principles governing the basis on which the Contractor is to price any new work (in the absence of competitive pricing). These principles are based on the concept of actual additional costs associated with the new work plus an agreed margin. - A key element of the evaluation process is to clarify ambiguities in tenderers’ proposals and/or the RFT. - Areas of scope and price needing clarification are scrutinised and discussed with tenderers during the negotiation process. |
| Contractor/Agency relationship. | - Information about Agency business priorities and its business environment was provided to tenderers during the tender process through RFT documentation (explanation of current IT&T environment and Agency business) and the due diligence process including: - written materials via a data room process (eg third party contracts, help desk reports, IT strategy plans etc); - site visits; - executive interviews; and - formal question and answer processes. - OASITO assisted Agencies in the due diligence process by: - providing Agencies with a Due Diligence Guide and conducting Due Diligence Workshops; - providing Agencies with a Due Diligence Materials Matrix to assist Agencies in identifying relevant types of data for due diligence; - assisting Agencies to obtain Third Party Consents; and - acting as the single point of communication between Agencies and tenderers. - In later processes OASITO encouraged greater opportunity for potential tenderers to interface with key Agency personnel to facilitate a greater understanding of high level strategic business issues. |
| Contractor resourcing | - OASITO developed a detailed evaluation methodology and process to assess each tenderer’s service capability that was approved by an independent probity auditor. - OASITO provided Agencies with a proforma Evaluation Guide and assisted Agencies tailor it to their requirements. - Agencies resourced the Evaluation Teams (ET) and OASITO assisted to train ETs in the evaluation process. - Agency ETs were responsible for signing off on the viability of the preferred tenderers’ technical, corporate and financial proposals. - Preferred tenderers were not selected until all significant business, financial, technical and legal issues were satisfactorily resolved (including tie down of all contract terms and pricing). - OASITO assisted Agencies in the provision of a secure Evaluation Centre. |
| Transition | - The ITO model ensured that significant detail concerning tenderers’ respective transition experience and specific plans are obtained during the evaluation process. - Tenderers were required to go through the rigour of articulating transition events in a detailed Transition Plan that addresses all key transition-related activities (and dependencies), a clear designation of responsibility for completing each activity, and key milestone dates by which those activities are to be completed. - Agencies and the Contractor signed off on the Transition Plan prior to transition. - The Contractor is not paid until the transition is completed to the satisfaction of the Group agencies. - OASITO performed an observer role and assisted Agencies where required. Management of the transition phase is the responsibility of Agencies. - The OASITO Contract Management Guide details a range of activities Agencies need to manage in this phase. - OASITO conducted workshops with Agencies and existing Contract Managers to share lessons learned from previous outsourcing transactions. |
| End user perceptions | - Agencies communicate to staff including how established practices will change when the Contractor takes over and be trained in the new service delivery processes that are to be implemented by the outsourcer (this applies to end users as well as the remaining IT staff). - Agencies establish clear processes for placing and prioritising service requests during transition are instituted. ## The OASITO Contract Management Guide outlined issues in this area. |
| Contractor performance | - The Services Agreement required the Contractor to provide a series of plans that Agencies can use as tools to manage the delivery of services, including: - Relationship Management Plan; - Transition Plan; - Procedures Manual (detailing at a day to day level how each service delivery process will be executed); - Documentation Plan (sets out what documents will be provided when during the life of the Agreement); - Compliance Procedures Plan; - Performance Management and Service Level Achievement Plans; - Benchmarking Plan (detailing how services will be benchmarked against best practice service delivery); - Technical Environment Change Control Plans; - Disengagement Assistance Plan; and - any other plan that agencies decide they require. - Agencies monitor compliance with internal obligations that affect Contractor performance. - If the Contractor does not perform, Agencies are able to levy service credits, remove services from scope, terminate the contract in whole or in part, seek services from third parties or perform functions itself. - The Contractor is required to commit to significant financial penalties (service credits) for breach of service levels. - In the event of non-performance by the Contractor (including where ‘force majeure’ events occur), Agencies are also entitled to have a third party step in on short notice to perform critical service functions during the period of non-performance at the expense of the Contractor. - The Services Agreement included a right for the Group to terminate the contract (in full or in part) at any time during the term without having to show cause. A negotiated termination fee may apply. - The Contractor is required to provide a detailed termination disengagement plan that requires the contractor to provide assistance to the Group to transfer services to another vendor or to bring the services in-house. - Disengagement Assistance includes provisions for the Contractor to ensure that all software licences are transferable or requires them to procure equivalent software licences for the Commonwealth and provide the Commonwealth or new vendor the option to purchase equipment at a reasonable price. |
| Technological change | - Services Agreements were signed for a five year period, consistent with “expert” recommendations to preserve flexibility by avoiding long term fixed contracts. The data telecommunications component is for a shorter period (2 or 3 years) in recognition of the rapid pace of change in the data carriage markets and telecommunications technology. - The Services Agreement included provisions requiring the Contractor to acknowledge that services will evolve over time and that Agencies do not pay for any consequent modification in the manner in which those services are provided. - Price certainty was achieved in Service Agreements wherever possible, including coverage for technical replacement and upgrades where possible. The Agreement has in-built mechanisms for managing obsolescence for different technologies ie: - Desktop upgrades are based on an end user equipment baseline reference point, with improvements in technology able to be passed on by either price or performance; - Midrange upgrades are ideally managed on a per unit/box reference price with changes and improvements in technology and performance passed on; - LAN upgrades are service level driven with the Contractor investing in infrastructure as it needs to in order to meet service levels. Agencies are not charged for such upgrades; and - Mainframe upgrades are ideally managed through usage based pricing. - The Services Agreement included a provision for independent benchmarking to ensure technology and performance are keeping pace with market norms. - The Services Agreement provided mechanisms for pricing new services that avoid open ended negotiations with the Contractor. - Importantly, the Services Agreement requires the Contractor to confirm that, if the Contractor charges another customer a lower price for similar services, it will adjust the Group’s service charges accordingly. - The Services Agreement requires the Contractor to allocate its charges among Group Agencies in a fair and equitable manner (eg based on the relative cost of service delivery to each Agency). |